Improving Grading and Assessment to Transform Learning

Agreement with San Leandro Unified School District (San Leandro, CA)

Background

San Leandro USD current initiatives are specifically designed to support the implementation of CCSS and to promote equitable educational opportunities (improved instruction, de-tracking, more efficient and effective delivery of special education services, and high school redesign). The District seeks to enter into a partnership with Crescendo Education Group to improve the accuracy and fairness of grading and assessment in order to fully support these initiatives. The District is choosing to begin this work with San Leandro High School, its comprehensive high school.

[Note: Based on the complexity of grading and assessment reform, this proposal assumes that 2015-16 is the first year of a multi-year partnership that would include additional schools. However, San Leandro USD and Crescendo Education Group are only entering into a 1-year partnership, extended upon mutual agreement.]

Outcomes (2- to 4-Year Plan)

### For teachers:

- All teachers use standards-based grading that is more accurate, fair, understandable to students, parents, and school staff, and reflecting proficiency on the Common Core standards

- Teachers understand relationships between standards-based grading practices, assessment, and instruction, and they can create and implement mutually-reinforcing and coherent practices

- Teachers have stronger collaborative relationships and experience a greater sense of efficacy with influencing student performance

### For students:

- Students can more accurately describe expectations for their academic outcomes, and their own place relative to those outcomes

- Students have a greater sense of agency and efficacy about their academic performance

- Students have a stronger sense of belief in their own success and of trust in their teachers

### For schools and the District as a system:

- Course passing rates increase and less grade inflation

- “Bottom-Up” support for schoolwide grading and assessment policies that are owned by teachers (i.e., the school administration does not need to create a top-down policy or be primarily responsible for enforcement)

- Increased capacity of school leaders to lead this work, with “proof points” of the value of improved formative assessment and grading practices

- Improved conversations with parent community about student expectations for Common Core standards mastery

Scope of Work

| Element | Content | When | Attendees and Structure | Crescendo Staff | Time |
| --- | --- | --- | --- | --- | --- |
| Pre-School Year Assessment | - Review 2014-15 syllabi and grades of Teacher Participants - Create survey to be administered to Teacher Participants, ideally before kick-off PD session - Identify trends and patterns across courses, teachers, grade levels | August 2015 | Data reviewed, disaggregated, and analyzed | JF (100%) | 1 day remotely |
| Pre-School Year Kick-Off | - Surface assumptions, beliefs, experiences about formative assessments and grading - Review history, function, and impact of traditional grading systems - Develop shared vision for grading and assessment - Discuss research and examine practices that more accurately and fairly assess and reflect what students know and can do on CCSS - Prepare for action research: - Each Teacher selects hypothesis and practice to prototype, with data collection plan | August 2015 | Teacher cohort from site and site leaders | JF (100%) | 1-1/2 days |
| Professional Development Sessions | For Teacher Participants: - Share action research results and identify next design - Additional research/practices for improved grading / assessment For Site Leaders: - Observe workshop to provide effective support to teachers | 6 workshops (Sept, Oct, Dec, Jan, Mar, May) | All teacher participants and Site Leadership | JF (80%) Associate (20%) | 1/2 day (3-hours) |
| Coaching of Teachers | - Provide differentiated, contextualized support for individual needs to ensure progress toward implementing improved grading practices - Informs monthly professional learning session content and provides feedback to Site Leader | 6 visits (Sept, Oct, Dec, Jan, Mar, May) | Teacher participants selected by Site Leadership or requesting assistance | JF (75%) Associate (25%) | 1 day preceding workshop |
| On-Call Support | - Provide problem-solving, resources, advice, and support to unique and specific questions | On-demand (response within 24 hrs) | Any Teacher Participant or Site Leadership | JF (75%) Associate (25%) | Bank of 10 hours |
| Presentation for Parents / Guardians | - Explanation of school’s work - Introduction to research base - Supported and co-facilitated by school representatives | October 2015 or March 2016 | School / District representative to co-facilitate | JF (100%) | 2 hours |
| Student Interviews | - Gather student voices and experiences - Share results with Teacher Participants and Site Leaders | Q1 | Students selected by Site Leadership | JF (100%) | Panel (2 hours) |
| Data Collection and Reporting | - Review grading data of Teacher Participants to identify trends, patterns, and comparisons to previous year - Share results with site leadership to discuss next steps - Semi-annual written summary of progress, challenges, and data outcomes to District administration with suggested next steps; followed by in-person discussion | End of each quarter | Data reviewed, disaggregated, and analyzed | JF (50%) Associate (50%) | 4 days remotely and on-site |
| District-wide presentation | - Share experiences and knowledge with other sites | 2 sessions: Jan, May | Representatives from different sites | JF (100%) | 2 hours each |

Data Sharing

A key to improving teachers’ grading and assessment is the ability to give them feedback on their progress, and how their progress is affecting students. For that reason, Crescendo Education Group works closely with the client to organize teachers’ grade data throughout the partnership. The attached Data Sharing Request describes the data needed, the process and timeline for receiving it, and our compliance with FERPA.

Project Cost:

Total project cost is $37,180 for 2015-16, based on an estimate of the work required for successful planning and implementation of the above scope.  This includes all materials and correspondence (pre-planning, debriefing) with site administrators and district administration, as well as all travel and related expenses.

Payment Schedule

Payment is to be made to Crescendo Education Group according to the following schedule (invoices will be sent during these months):

- 50% at work launch (August)

- 50% at mid-point of work (February)

Signed parties agree to the terms and conditions of this contract. Any material adjustment to the terms of this contract is to be made in writing and agreed upon by both parties.

____________________________					____________

Joseph Feldman, CEO							Date

Crescendo Education Group

____________________________					____________

Dr. Rosanna Mucetti, Deputy Superintendent Ed Services		Date

San Leandro Unified School District

NOTE: This Agreement is incomplete without submission of Crescendo Education Group’s Data Sharing Request