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 SEQ CHAPTER \h \r 1AMENDMENT #4
ArchitectURAL SERVICES


This “AMENDMENT” made and entered into this October 13, 2015 by and between San Leandro Unified School District, a political subdivision of the State of California, herein called “District” and the “Architect”.
WLC Architects, Inc.
2600 Tenth Street, Suite 500
Berkeley, CA 94710

Kevin A. MacQuarrie, Principal in Charge
Whereas, the parties entered into an agreement on March 16th,  2011 whereby Architect was to provide architectural services in connection with SLHS Swim Center, Track & Field Projects (Agreement); and Now therefore the parties agree to amend and modify the Agreement as follows: 
1.0 
DESCRIPTION OF AMENDMENT #4
This Amendment modifies the Agreement, Article 5.1, Exhibit A and Exhibit C, due to additional architectural and engineering services requested, as follows:

ASA 2 - Establish survey control points 






$2,750

ASA 3 – Survey topo between gymnasium and existing portables 



$5,950

ASA 4 – Additional drinking fountains at swimming pool deck  



$1, 825

ASA 7 – Review conformance survey/as-built conditions; provide sub-drainage plan 

$8,416

Total, full and final architectural and engineering services = 



           $18,941

To the extent that this Amendment conflicts with any of the provisions of the Agreement, the terms and conditions of this Amendment shall have precedence. To the extent that any ambiguity or conflict is created by this Amendment as to the services and/or deliverables to be provided by the Architect, the provision shall be given the interpretation most favorable to the District.
2.0 
COMPENSATION
The original Agreement was in the amount of $750,000, previous amendments brought the Not to Exceed Fee prior to this amendment to $1,191,555.  This Amendment #4 of $18,941 brings to $1,210,496.   


IN WITNESS WHEREOF, the parties have caused this Agreement to be duly executed this ________ day of ___________________, 2015.

Architect




District

By:
____________________________

By:
______________________________
 Kevin A. MacQuarrie, Principal


 San Leandro Unified School District
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