Joanne Clark

San Leandro Unified School District

San Leandro, CA 94577

February 1, 2016

RE: Bancroft Middle School CanSat Program and Budget

Hi Joanne –

We are excited to be working with San Leandro GATE students to create an amazing experience in STEM education for Bancroft Middle School for the 2016 spring semester.

This letter is a summary of our conversations and provides milestones, primary objectives, and budgeting. Up to 32 students will participate in the program this spring after school through the Bancroft Middle School GATE initiative at the Barbara Lee Center Thursday afternoons beginning in February 25, 2016 through May 31, 2016. The project will culminate with the launch of a high-altitude balloon on May 25, 2016 at San Leandro High.

Budget

| Quantity | Price | Near Term Item | Total |
| --- | --- | --- | --- |
| 1 | $2,500 | 8 Classroom Science and Math CanSats. Hardware & Curriculum. 3D printed shell included | $2,500 |
| 0.33 | $2,500 | High Altitude Balloon Flight - Includes FAA clearance, logistics, hardware support, tracking and recovery | $825 |
| 40 | $40 | 40 total hours of support Includes a minimum of 1 day/month in district for support, and reporting. | $1,600 |
|  |  | Subtotal | $4,925 |

Professional Development

We begin our work with a Professional Development Introduction for instructors where teachers will cover 3 subject domains: Hardware, Software and Analytics, and mapping to Next Generation Science Standards. This introduction is optional but highly recommended for optimal use in the classroom setting. The workshop will be held on February 11, 2016 at the Barbara Lee Center for Health and Wellness between 3:30 and 5:00 pm.

Program Schedule

CanSat hardware will be available at the Barbara Lee Center on or before February 25, 2016. Chromebooks with Internet access will be required for each student team (up to 4 students per team).

Classes will be held at the Barbara Lee Center (BLC) for Bancroft students on Thursdays from 3:30 to 5:00 pm. The school will coordinate travel from Bancroft Middle to the BLC.

| SESSION |  | DATE | SESSION |
| --- | --- | --- | --- |
| Teacher's Introduction |  | 5-Apr | JMM - Magnetometer |
| JMM - Hardware/Software Intro |  | 7-Apr | BLC - Magnetometer |
| BLC - Hardware/Software Intro |  | 12-Apr | JMM - Magnetometer |
|  |  | 14-Apr | BLC - Magnetometer |
| JMM - Barometric |  | 19-Apr | JMM - GPS |
| BLC - Barometric |  | 21-Apr | BLC - GPS |
| JMM - Barometric |  | 26-Apr | JMM - GPS |
| BLC - Barometric |  | 28-Apr | BLC - GPS |
| JMM - Temp/Humidity |  |  |  |
| BLC - Temp/Humidity |  | 3-May | JMM - Air Quality / Weather |
| JMM - Temp/Humidity |  | 5-May | BLC - Air Quality / Weather |
| BLC - Temp/Humidity |  | 10-May | JMM - Air Quality / Weather |
|  |  | 12-May | BLC - Air Quality / Weather |
|  |  | 17-May | JMM - Predictions |
|  |  | 19-May | BLC - Predictions |
|  |  | 24-May | JMM - Preparation |
|  |  | 25-May | High Altitude Balloon Launch |
|  |  | 26-May | JMM - Report |
|  |  | 31-May | BLC - Reports |

Flight Readiness and Launch Experience

Magnitude will work with the teachers and students to ensure each school group is prepared for the high altitude balloon experience.

Support

Magnitude will provide online support by email or phone during the school year. It will collaborate with San Leandro Unified teaching staff to develop supplemental tracks based on the interest, goals, and objectives of each individual teacher and their program. In addition, Magnitude will be in district at least once per month to gather feedback, answer questions, and attend a monthly project review meeting.

Mapping to the New Standards

The Magnitude program is a modular, multi-disciplinary framework that is guided by the Next Generation Science Standards 3-dimensions architecture. This includes Science and Engineering Practices (SEPs), Disciplinary Core Ideas (DCIs), and Crosscutting Concepts (CCCs) for grades 7 and 8 in this first year cohort, and engagement and support for grades 9-12 under the same NGSS framework.

The Magnitude framework engages through Science and Engineering Practices:

- Asking questions and defining problems

- Planning and carrying out investigations

- Analyzing and interpreting data

- Developing and using models

- Constructing explanations and designing solutions

- Engaging in argument from evidence

- Using mathematics and computational thinking

- Obtaining, evaluating, and communicating information

With the addition of the optional International Space Station experiments beginning Fall 2016, the program touches on every Disciplinary Core Idea:

- Physical Science

  - Matter and its interactions

  - Motion and stability: forces and interaction

  - Energy

  - Waves and their applications in technologies for information transfer

- Earth and Space Science

  - Earth’s place in the universe

  - Earth’s systems

  - Earth and human activity

- Engineering Technology and the Application of Science

  - Engineering design

  - Links among Engineering, Technology, Science, and Society

- Life Science (optional – Fall 2016)

  - From molecules to organisms: structures and processes

  - Ecosystems: interactions, energy, and dynamics

  - Heredity: inheritance and variation of traits

  - Biological evolution: unity and diversity

We are thrilled to be working alongside you, your staff, teachers, and students in this ground breaking program. Please let us know if you have any questions. Our virtual door is always open.

A posse ad esse!

- Ted Tagami